## Datatypes in Java
Ticket | Summary | Assignee | Reporter | Status | Points to be discussed | Work Logged on Current | Planned Duration | Remaining Estaimation | Estimation Comments | Target Date
GC-1051 | gc_kram : implement accès à BDL | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | Closed |  |  | 0m | 0m
GC-1086 | gc_enrichapplication : check that Active MQ is down | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | Closed |  |  | 0m | 0m
GC-1101 | tool to give GFU | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | Closed |  |  | 0m | 2h
UT-96 | develop ut_maillistmanager, part 1 | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | Closed |  |  | 2d | 0m
LEX-4128 | delete rosetta to jira log | Baskar, Shakila Rani (Infosys) | Vandwalle, Julien (LNG-PAR) | Closed |  |  | 2h | 0m
UT-98 | development of to_updategfuforjp20 | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | In progress |  |  | 0m | 2d
UT-97 | develop to_maillistmanager, part 2 | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | In progress |  |  | 0m | 1d
GC-1087 | supervision of reference loading | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | In testing |  |  | 0m | 0m
SRC-1142 | JURICA - Alerte par Mail en cas de retard de livraison des fichier XML par le prestataire | Kasim, Shaik Rizwan (Infosys) | Farzollahi, Mohammad (LNG-PAR) | In progress |  |  | 0m | 4h
FC-506 | production JK_DEC for element from producteur SAJD are not converted | Kasim, Shaik Rizwan (Infosys) | HORNN, AI QUOC DANIEL (LNG-PAR) | In progress |  |  | 4d | 0m
FC-475 | apply needed changes for JP_2_0 on profil document - create case:references | Kasim, Shaik Rizwan (Infosys) | HORNN, AI QUOC DANIEL (LNG-PAR) | In testing |  |  | 1d 4h | 0m
FC-440 | Part 3 : Revue XSL - java - complete XSL to achieve conversion | Kasim, Shaik Rizwan (Infosys) | Lefebvre, Christophe (LNG-PAR) | In testing |  |  | 3d | 0m
FC-474 | JP_2_0 : apply the needed changes on XSLT to match the expected output | Kasim, Shaik Rizwan (Infosys) | HORNN, AI QUOC DANIEL (LNG-PAR) | In testing |  |  | 1d | 0m
FC-453 | Change the way the SGML to XML conversion is implemented | Kasim, Shaik Rizwan (Infosys) | Lefebvre, Christophe (LNG-PAR) | In testing |  |  | 2d | 0m
TS-513 | Fusion de branches ts_conversion | Ummer Faruk, Shaik (Infosys) | Lefebvre, Christophe (LNG-PAR) | In Progress |  |  | 2h | 2h
BO-1427 | suivi infosys | Ummer Faruk, Shaik (Infosys) | Ummer Faruk, Shaik (Infosys) | Resolved |  |  | 1w | 0m
GC-913 | gc_link : dtd manquantes | Ummer Faruk, Shaik (Infosys) | Dzuba, Vassili (LNG-PAR) | In testing |  |  | 2h | 0m