## Datatypes in Java
Ticket | Summary | Assignee | Reporter | Status | Points to be discussed | Work Logged on Current | Planned Duration | Remaining Estaimation | Estimation Comments | Target Date
GC-1095 | see specs in : http://confluence.lexisnexis.fr/display/~DZUBAV/to_storecopy+%3A+setting+of+GFU | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | Resolved | comments | 1d | 0m | 4h | est Comments
FC-520 | *goals* : - handled nullpointerexception *how* : - you need to handle it with catching the exception - add a warn message in logs - still on the branches FC-411 | Baskar, Shakila Rani (Infosys) | HORNN, AI QUOC DANIEL (LNG-PAR) | Closed | comments | 2d | 2d | 0m | est Comments
LEX-4128 | Logs of jira process in rosetta have to be deleted | Baskar, Shakila Rani (Infosys) | Vandwalle, Julien (LNG-PAR) | Closed | comments | 1h 1m | 2h | 0m | est Comments
GC-1101 | goal ; to write a simple command-line program to set the GFU on a set of documents in Documentum (using gc_store) the command takes as parameter a list of kids, or a filenalme (prefixed as usual by @) that contains a list of kids. The documents whose kids are specified will have their gfu set to the current date/time (using gc_store). | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | In progress | comments | 1d 3h | 0m | 2h | est Comments
UT-96 | specs are in : [http://confluence.lexisnexis.fr/display/~DZUBAV/Mail+list+manager] This Jira include steps 1 and 2 in the specs. | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | In progress | comments | 1w 5h | 2d | 0m | est Comments
GC-1051 | Specs are in : http://confluence.lexisnexis.fr/display/~DZUBAV/KRAM+interface+to+BDL+database | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | In testing | comments | 1d 4h | 0m | 0m | est Comments
GC-1087 | See specs at address : http://confluence.lexisnexis.fr/display/~DZUBAV/Reference+import+supervision | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | In testing | comments | 3d | 0m | 0m | est Comments
GC-1086 | When the Active MQ service crashes (that already occurred once ot twice), we currently don't have any mean to detect the situation. As a consequence, the supervision workflow is unable to get the kids of the document to process from its input queueL, and as a result the documents go to the platform without the enrichments. So we want the application to check the status of ActiveMQ and send a mail to the administrator if it is down. | Baskar, Shakila Rani (Infosys) | Dzuba, Vassili (LNG-PAR) | In testing | comments | 3d | 0m | 0m | est Comments
SRC-1142 | JURICA Afin qu'on soit alerter par un mail en cas de retard de livraison par le prestataire, un mail d'alerte doit être envoyé per le programme à l'équipe de production. Mohammad | Kasim, Shaik Rizwan (Infosys) | Farzollahi, Mohammad (LNG-PAR) | In progress | comments | 3d 4h | 0m | 1d | est Comments
FC-506 | context : - conversion FTK - AllFcFtkConverters issue : - lot PRODUCTION : \\lngpark4cp111v\Rosfab\Conversion\Sources\JPKIND\PRO_481229 unit test should be passed to green : SVN branch : http://intrasvn.lexisnexis.fr/svn/svn_fc/branches/AllFcFTKConverters/FC-506 Awaited : - Add new test unit to process lot : AllFcFTKConverters\fc_jp_2_0\src\test\resources\PRO_481229 - Assert that file generated should be like 90% of the awaited - Report in a sum-up the difference in order to know if the difference is normal or not (to complete the xslt) | Kasim, Shaik Rizwan (Infosys) | HORNN, AI QUOC DANIEL (LNG-PAR) | In progress | comments | 1w 1d | 4d | 0m | est Comments
FC-475 | *goals* : - expected output is change for 1 document - you need to apply the changes without modifying the decision part - inside the "case:references" for profil, you should call the java method "getLinksIdsFromRdfWithQualifierForTexteFondateur()" 2 times. 1st time with qualifier : "lnf:dsc#QRSC_QRSCTXTVISEVISAS" to create a block , where $idrenvoi is each item return by the method {code} <case:references searchtype="VISA" referencetype="legislation"> <xsl:apply-templates select="//sourcejurisfr//renv:rtnc[@id = $idrenvoi] ¦ //sourcejurisfr//renv:rtc[@id = $idrenvoi]" /> </case:references> {code} 2nd time with qualifier : "lnf:dsc#QRSC_QRSCTXTVISEMOT" to create a block , where $idrenvoi is each item return by the method {code} <case:references searchtype="MOTIF" referencetype="legislation"> <xsl:apply-templates select="//sourcejurisfr//renv:rtnc[@id = $idrenvoi] ¦ //sourcejurisfr//renv:rtc[@id = $idrenvoi]" /> </case:references> {code} as reminder : 1 input (decision) 2 output (decision , profil) SVN branches : http://intrasvn.lexisnexis.fr/svn/svn_fc/branches/AllFcFTKConverters/1.1.3-FC-444 module : fc_jp_2_0 | Kasim, Shaik Rizwan (Infosys) | HORNN, AI QUOC DANIEL (LNG-PAR) | In testing | comments | 2d 4h | 1d 4h | 0m | est Comments
FC-440 | *context of this task*: - achieve to remove the current conversion (written in omnimark software) into java+xsl *svn project* branches : [http://intrasvn.lexisnexis.fr/svn/svn_fc/branches/RevueXSL_LNJC/FC-374] - it'll be create on 2017-05-15 (paris afternoon) *goals* : - complete XSLT in order to make tests regression goes green - tests units do the following : -- launch the conversion over a bundle of documents -- for each documents generated, it compares to an awaited xml --- if xml not "similar" then .. tests failed *delivery and expectations* : - updated xsl - updated java method (if needed) - complete if necessary tests units with methods use on XSLT | Kasim, Shaik Rizwan (Infosys) | Lefebvre, Christophe (LNG-PAR) | In testing | comments | 4w 3d 4h 1m | 3d | 0m | est Comments
FC-474 | *context* : - the xml output expected has been changed. *delivery* : - xslt for jp_2_0 - changes should only be seen on new document generated "the profil" (document filename endeds with "_1_0KRH.xml") *SVN branches* : http://intrasvn.lexisnexis.fr/svn/svn_fc/branches/AllFcFTKConverters/1.1.3-FC-444 module fc_jp_2_0 | Kasim, Shaik Rizwan (Infosys) | HORNN, AI QUOC DANIEL (LNG-PAR) | In testing | comments | 2d | 1d | 0m | est Comments
FC-453 | The Encyclopedie conversion handles SGML documents. Prior to the real conversion, the documents are transformed to XML. The current conversion uses the class Sgm2XML in /EncycloXSL_LNJC/src/main/java/com/lnf/EncycloRosetta.java The goal of this JIRA is to handle this conversion through the use of a service. The conversion service call will be configurable in the application.properties. For ex : conversion.server=http://cert.intrasie.lexisnexis.fr/api/cc/conversion_sgml-xml_interne/1.0/ conversion.username=secured conversion.password=foo conversion.timeout=10000 A client for this service can be found in http://intrasvn.lexisnexis.fr/svn/svn_cc/trunk/cc_convert-ee_client DEV can be done in the existing branch http://intrasvn.lexisnexis.fr/svn/svn_fc/branches/EncycloXSL_LNJC/FC-372 | Kasim, Shaik Rizwan (Infosys) | Lefebvre, Christophe (LNG-PAR) | In testing | comments | 2w 1d 1m | 2d | 0m | est Comments
TS-492 | The conversion of LEGIDILA TnC does not handle the following elements/attributes For TEXTELR and TEXTE_VERSION input DTD - META_SPEC/META_TEXTE_CHRONICLE/NUM_PARUTION should be converted to a <mt:metasource> - VERSION/LIEN_TXT/@num should be converted to *TO BE PRECISED* For ARTICLE and SECTION_TA input DTD - CONTEXTE/TEXTE/@num_parution_jo should be converted to a <mt:metasource> - table/@border should be converted to the proper KIND element The backward conversion does not handle the following element/attributes - <cnt: p> and <cnt:br> when child of VISAS, SIGNATAIRES, NOTA should be converted to <p> and <br> - The normalisation should convert <div> to <p> when child of VISAS, SIGNATAIRES, NOTA - This particular element doesnt seem to be properly converted back <mt:metasource cle="/ARTICLE[1]/CONTEXTE[1]/TEXTE[1]/@num" clelnf="num" valeur=""/> When converted we don't have an empty attribute, but an attribute with a space <TEXTE num=" "> | Ummer Faruk, Shaik (Infosys) | Lefebvre, Christophe (LNG-PAR) | Resolved | comments | 1w 1d | 2d | 0m | est Comments
TS-508 | 1) Change the way the OCR is configurable. We want it to be dynamically configured by using propertiesAsText Exemple of content of propertiesAsText {code} conversion.lang=fra conversion.enable.userwords = true conversion.segmentation.mode = true {code} Make sure the format of propertiesAsText is the same than used for other uses (is in convert()). I didn't check how it is exactly. 2) Is it possible to have more than one langage for the dictionary filter ? Ex : conversion.lang=fra,mar | Ummer Faruk, Shaik (Infosys) | Lefebvre, Christophe (LNG-PAR) | Resolved | comments | 2d | 2d | 1d | est Comments
FC-480 | *description of the project* : - in order to simulate the whole environment FTK (without persistence) there's a project that let user to select - short brief of the project : http://confluence.lexisnexis.fr/display/FTKL/FTK+Light *issue* : - when controlcenter try to mount up a ftklight instance.. all system out from running jetty start is loss - the fact that we don't see those messages from launching the jetty server for the instance is a big lack of information to debug why the instance don't up *goals* : - when controlcenter launch the external command "mvn jetty:run" to launch the ftklight-instance mount ... all message from that launch should redirected to LOGS | Ummer Faruk, Shaik (Infosys) | HORNN, AI QUOC DANIEL (LNG-PAR) | Closed | comments | 4d | 2d | 0m | est Comments
BO-1427 |  | Ummer Faruk, Shaik (Infosys) | Ummer Faruk, Shaik (Infosys) | In progress | comments | 4d | 1w | 0m | est Comments
GC-1099 | At the moment, the structuration service only takes one paragraph into account, to determine its type. We need to be able to add the context of the previous paragraph in a one case (this use may be generalized later). So we need to add this exceptions. If the configuration file used is CE and that the pattern is either "Sur le", "Sur la" or "Sur les" and that the previous not empty paragraph content was "Il soutient que :" Then we return no type (StringUtils.EMPTY) I propose to add these informations to the configuration file. Ie {code}<pattern case="loose" match="Sur le" structure="motif"/> {code} would become {code}<pattern case="loose" match="Sur le" notfollowing="Il soutient que :" structure="motif"/> {code} | Ummer Faruk, Shaik (Infosys) | Lefebvre, Christophe (LNG-PAR) | In progress | comments | 2d | 2d | 4h | est Comments
GC-913 | envoyer un message clair si la DTD est manquante. A l'heure actuelle, on reçoit une NPE. | Ummer Faruk, Shaik (Infosys) | Dzuba, Vassili (LNG-PAR) | In testing | comments | 1m | 2h | 0m | est Comments